## Minimum Reqs
Project Name
Sustainability Requirements Tracking Matrix
This document shall used to track the SAIT Sustainability Requirements, and the strategies to achieve them on the project. The document shall be updated regularly as needed during design and construction, based on the most recent design documents and information provided by the design team. The document does not represent a final documentation of sustainability performance, but shall be accurate based on the information provided as of the date shown.
Minimum Requirements | [5 empty] | Updated: 10-6-2022
Topic | Requirement Summary | Deliverables | Strategies | Update | Responsibilities | Compliance Status
1. Integrated Design | 1.1 Integrated Design: Follow an integrated design process that creates synergies across disciplines for higher level of sustainability performance. | A Visioning Workshop meeting output summarizing the Project Vision, Energy and GHG Reduction Targets, Affirmation of Intent to Achieve Minimum Sustainability Requirements, Questions and Action Items for Design Stage, Opportunities for Innovation and Living Lab. All subsequent Sustainable Design coordination meeting shall produce an output summarizing items discussed, including update on sustainability requirements. | 1.1.1 Conduct an integrated design Visioning Workshop during the Pre-Design or Concept Design stage which includes the full range of applicable design disciplines and owner representatives.
1.1.2 During Schematic Design, host a Sustainable Design coordination meeting to update status on sustainability requirements.
1.1.3 During Design Development, host a Sustainable Design coordination meeting to update status on sustainability requirements.
1.1.4 During Construction Documents, host a Sustainable Design coordination meeting to update status on sustainability requirements.
2. Energy and Carbon | 2.1 Energy Performance: For all new constructions and major renovations, achieve an energy use reduction and GHG emissions reduction of at least 15% better than National Energy Code for Buildings (NECB) 2017 baseline. | At Pre-Design stage, issue an Energy Concepts Report which identifies energy benchmarking information, energy target setting, major energy end uses (and sources of operation GHG emissions), and preliminary list of opportunities for Energy Conservation Measures (ECMs). An energy modeling report for each design stage (100% Schematic Design, 100% Design Development, 100% Construction Documents) which demonstrates whether the targeted energy savings % is being achieved is to be signed by the Energy Modeler or Mechanical Engineer and submitted to the Project Manager. | 2.1.1 Benchmarking and target setting - Compare the facility to other completed comparable facilities to identify useful data for EUI (kWh/m2) and % savings vs. energy standards & codes.
2.1.2 Early Stage Energy Modeling - Conduct a Schematic-level energy model for preliminary goal setting and evaluation of architectural strategies.
2.1.3 Energy Conservation Measures - Evaluate and identify strategies to improve energy performance to realign with project targets.
2.1.3 DD Energy Modeling - Evaluate envelope performance, lighting power densities, mechanical systems and other components for contribution to energy performance, operations, business case, and % NECB target.
2.1.5 Final Design Energy Modeling - Provide an energy model report based on 100% CD documents and final selections for glazing, HVAC, lighting, control sequences, etc.
| 2.2 Lighting Power Density: For all major renovations and minor renovations, achieve a reduction in Lighting Power Density (LPD) of at least 25% below the maximum allowances of NECB 2017 | Lighting power density calculations. | 2.2.1 Evaluate allowable lighting power densities and identify opportunities to reduce lighting power densities early in the design process.
| 2.3 Commissioning: Complete enhanced commissioning for the major energy consuming systems, energy generation systems and the building envelope as per the Fundamental Commissioning pre-requisite and Enhanced Commissioning credit defined in the Leadership in Energy and Environmental Design (LEED) V4 reference manual. | Deliverables defined in the LEED V4 Fundamental and Enhanced Commissioning prerequisite and credit are to be submitted to the Project Manager. | 2.3.1 Commissioning Authority (CxA) - Appoint a commissioning authority, before the end of design development stage, to coordinate and complete commissioning activites on the project.
| 2.4 Enhanced Refrigerant Management: Use either low-impact refrigerants or no refrigerants. Select systems with refrigerants that meet the requirements of the 'Enhanced Refrigerant Management' credit of LEED v4 BD+C. | Submit to the Project Manager: • Refrigerant product datasheets for used refrigerants • Calculations demonstrating GWP and ODP of project refrigerants | 2.4.1 Benchmarking / Feasibility: Mechanical engineering team to provide experience of similar facilities; feasibility of meeting LEED Refrigerant requirements.
2.4.2 Evaluation of refrigeration equipment.
| 2.5 Energy Metering: During Design Development Stage, confirm the project requirements for energy metering, submetering, reporting, and smart building integration and develop a preliminary Energy Metering Plan. | If applicable, develop a preliminary Energy Meterign Plan with a list of meters to be installed, including type, energy source metred along with manufacturers' cutsheet. Update the Energy Metering Plan during Construction Dcuments. | 2.5.1 Identify sources and end uses that require energy metering.
2.5.2 Formalize the Energy Metering Plan for submission and approval in the 100% Design Development Stage.
2.5.3 Update the Plan during Construction Dcuments for comment and approval.
| 2.6 Energy Star Appliances: All refrigerators and ice machines shall be ENERGY STAR rated and no more than 5 model years old. | Submit product cutsheets demonstrating compliance with the requirements to the Project Manager. | 2.6.1 Select appliances that meet the requirements outlined.
3. Health, Wellness and Indoor Environmental Quality | 3.1 Construction Indoor Air Quality (IAQ) Management: Develop and implement an IAQ Management plan for project construction. The IAQ management plan should align with the approach and considerations identified in the Sheet Metal and Air Conditioning National Contractors Association (SMACNA)’s IAQ Guidelines for Occupied Buildings Under Construction, 2007 (chapter 3) and LEED V4 credit Construction Indoor Air Quality Management Plan. | Prior to construction, the prime contractor shall develop and submit an IAQ management plan outlining how the contractor will maintain good indoor air quality. The prime contractor shall also provide construction photos demonstrating compliance with the IAQ plan taken intermittently throughout construction. | 3.1.1 Contractor Design Kick-off - Facilitate meeting with contractor to discuss requirements.
3.1.2 Specifications - Include Construction IAQ Management requirements in the specifications.
| 3.2 GBT Product Directory: Use the Green Building Technologies (GBT) Product Directory as a resource while making material selections where possible. The Product Directory contains a list of preferred materials and effort should be made to incorporate materials from the list where feasible. | List of products from the GBT Product Directory that were used on the project. | 3.2.1 Review the GBT Product Directory and specify products from the list where feasible.
4. Materials and Waste | 4.1 Construction and Demolition Waste Management: Divert at least 80% of non-hazardous construction and demolition waste from landfill. | A Construction Waste Management Plan is to be created and submitted by the Prime Contractor to the Project Manager. Waste diversion tracking sheets identifying overall diversion rates, and that break out each shipment / delivery with associated material streams, diversion rates and diversion destinations shall also be provided to the Project Manager. | 4.1.1 Contractor Design Kick-off - Facilitate meeting with contractor to discuss requirements.
4.1.2 Specifications - Include waste diversion requirements in the specifications.
| 4.2 Recycled Materials and Local Materials: Evaluate material and product options to identify potential to incorporate recycled materials and local materials that are regionally extracted, processed, and manufactured. | List of major products or materials that were recycled or regionally sourced. | 4.2.1 Review preliminary design concepts and identify opportunities to use recycled or local materials.
4.2.2 At each design submission, summarize major products or materials that are selected to be recycled materials or regionally sourced.
4.2.3 During construction, track major products and materials that are recycled materials or regionally sourced.
| 4.3 Embodied Carbon: At the completion of Pre-Design, identify embodied carbon benchmarking information, embodied carbon reduction target setting, anticipated major sources of embodied carbon impact, and preliminary list of opportunities for Embodied Carbon Reduction Measures. Incorporate measures to reduce Embodied Carbon of Construction. If Lifecycle Analysis (LCA) is within scope of work, target a reduction of 20% in embodied carbon. | For new buildings and major renovations at the completion of Pre-Design stage, issue an Embodied Carbon Reduction Report (ECRR). Update the ECRR and submit for review at the completion of each design stage (100% Schematic Design, 100% Design Development, 100% Construction Documents). If LCA is within scope of work, include LCA results within the ECRR updates at each design stage (100% Schematic Design, 100% Design Development, 100% Construction Documents). | 4.3.1 During Concept and Schematic Design phases, conduct comparative studies of structural materials as well as cladding materials to understand the relative impact of material selections on embodied carbon. Conduct additional research as needed in subsequent phases.
4.3.2 If applicable, starting at Schematic Design phase and then subsequent phases, conduct a whole building life-cycle assessment (LCA) to determine the preliminary embodied carbon for the project.
4.3.3 Implement the strategies recommended from research and LCA activities to reduce the embodied carbon of construction on the project.
5. Landscape and Biodiversity | 5.1 Responsible Landscaping: Design project landscaping in a manner that reduces or eliminates potable water consumption for irrigation by 50% by minimizing turf grass and installing native and drought-tolerant plants, provides habitat for local wildlife, and provides occupants with access to nature. | Provide a description of the proposed approach to comply with the requirements. Provide Landscape, Irrigation and Civil drawings to the Project Manager. | 5.1.1 Consider strategies including but not limited to smart irrigation, retention of stormwater, drought tolerant native vegetation, supporting of local fauna and minimization of turf grass.
5.1.2 Consider irrigation with Captured Rainwater.
6 Water and Resources | 6.1: Indoor Water Use: Achieve a minimum designed non-process plumbing fixture water savings of 35% above the defined baseline in LEED V4. For process equipment: • All dish washers and clothes washers shall be Energy Star rated; • Do not use once-through cooling with potable water for any equipment or appliances that reject heat. | Submit water fixture product data sheets and completed water use calculations demonstrating compliance with the above requirements to the Project Manager. | 6.1.1 Mechanical engineering team to provide experience of similar facilities; feasibility of meeting 35% water savings.
6.1.2 Run water use calculations based on preliminary occupancy estimates and fixture flow rate selections.
6.1.3 Low-Flow Fixtures: Indicated flow rates in the Schematic Design report and discuss at sustainability workshops.
| 6.2 Stormwater Management: If pursued, manage stormwater on-site using green stormwater infrastructure. Satisfy one of the following two compliance options: Option 1: Percentile of Rainfall Events • All Projects – Manage on site the runoff from the developed site for 80th percentile of local rainfall events. Zero Lot Line Projects Only – Manage on site the runoff from the developed site for 70th percentile of local rainfall events. Option 2: Natural Land Cover Conditions • Manage on site the annual increase in runoff from the natural land cover condition to the post-development condition. | Calculations demonstrating compliance with the requirements should be submitted to the Project Manager. | 6.2.1 Evaluate opportunities for on-site treatment of rainwater early in the design process.
6.2.2 Run SWM treatment calculations to update % runoff treated onsite. Provide option(s) for SWM infrastructure to meet requirements.
7 Tracking, Reporting and Feedback | 7.1 Sustainable Design Reports: At the completion of each design stage, submit a Sustainable Design Report including a copy of the Sustainability Tracking Matrix for review and sign-off by the Project Manager which summarizes the status of each Minimum Requirement and any other sustainability initiatives. | A Sustainable Design Report including a copy of the Sustainability Tracking Matrix at the completion of each design stage. | 7.1.1 During each design stage, compile all information related to sustainability including project aspirations, design features, workshop summaries, energy modeling reports, ECRRs and LCA results (if applicable) to be included in the Sustainable Design Report.
| 7.2 Data Reporting: Report data needed to complete the reporting for the STARS program. | Information on the STARS program and the data required can be found here: (Include link to STARS information requirement) | N/A
Updated: 10-6-2022